## Project Plan
Project_id | Project_name | Milestones | Description | Owner | Start_date | End_date | Status | Priority | Progress_percentage | Created_at | Updated_at
PROJECT_ID | PROJECT_NAME | Kickoff & Requirements | Run kickoff meetings with the client, document business goals, user requirements, success metrics, and a prioritized feature list. Done means a signed requirements document and acceptance of scope and timelines by the client. | Aarav Sharma | 2026-07-03 | 2026-07-09 | Not Started | High | 0 | 2026-07-03T16:26:08.729+05:30 | 2026-07-03T16:26:08.729+05:30
PROJECT_ID | PROJECT_NAME | UX Wireframes & Journeys | Produce user journeys, sitemap, and low-fidelity wireframes for key flows (browse, search, product page, cart, checkout). Done means approved wireframes and flow diagrams for development and design handoff. | Rohan Mehta | 2026-07-10 | 2026-07-17 | Not Started | High | 0 | 2026-07-03T16:26:08.729+05:30 | 2026-07-03T16:26:08.729+05:30
PROJECT_ID | PROJECT_NAME | Visual Design & Brand Assets | Create high-fidelity page designs, responsive layouts, and brand assets (banners, icons, product image guidelines). Done means final design files and an asset package delivered for implementation. | Vikram Desai | 2026-07-16 | 2026-07-27 | Not Started | Medium | 0 | 2026-07-03T16:26:08.729+05:30 | 2026-07-03T16:26:08.729+05:30
PROJECT_ID | PROJECT_NAME | Frontend Development | Implement responsive UI components, pages, and client-side interactions (React), integrating design assets and connecting to APIs. Done means a fully functional frontend deployed to a staging environment matching designs and passing visual review. | Neha Verma | 2026-07-20 | 2026-08-17 | Not Started | Critical | 0 | 2026-07-03T16:26:08.729+05:30 | 2026-07-03T16:26:08.729+05:30
PROJECT_ID | PROJECT_NAME | Backend & Integrations | Build APIs, database schema, authentication, payment gateway, and third-party integrations required for e-commerce operations. Done means backend deployed to staging with working APIs, secure auth, and payment test integration. | Karan Singh | 2026-07-27 | 2026-08-24 | Not Started | Critical | 0 | 2026-07-03T16:26:08.729+05:30 | 2026-07-03T16:26:08.729+05:30
PROJECT_ID | PROJECT_NAME | Product Catalog & CMS Setup | Configure product data model, import initial shoe catalog, set up admin CMS workflows and pricing/variant controls. Done means product catalog imported, CMS users configured, and content entry workflows documented. | Ananya Gupta | 2026-08-03 | 2026-08-21 | Not Started | High | 0 | 2026-07-03T16:26:08.729+05:30 | 2026-07-03T16:26:08.729+05:30
PROJECT_ID | PROJECT_NAME | SEO & Product Content | Create SEO-focused product descriptions, landing page copy, meta tags, and initial blog/landing content for launch. Done means all product pages and key landing pages have reviewed, SEO-optimized copy uploaded to staging. | Simran Kaur | 2026-08-10 | 2026-08-24 | Not Started | Medium | 0 | 2026-07-03T16:26:08.729+05:30 | 2026-07-03T16:26:08.729+05:30
PROJECT_ID | PROJECT_NAME | QA, Testing & Bug Fixes | Execute functional, cross-browser, performance, and payment flow testing, log issues, and resolve critical bugs. Done means all critical/blocker issues resolved, regression testing passed, and signoff for production readiness. | Priya Patel | 2026-08-17 | 2026-08-31 | Not Started | Critical | 0 | 2026-07-03T16:26:08.729+05:30 | 2026-07-03T16:26:08.729+05:30
PROJECT_ID | PROJECT_NAME | Launch, Deployment & Handover | Deploy the site to production, run final smoke tests, hand over credentials and documentation, and provide a short launch support window. Done means production site live, deployment checklist completed, and client acceptance recorded. | Aarav Sharma | 2026-09-01 | 2026-09-03 | Not Started | Critical | 0 | 2026-07-03T16:26:08.729+05:30 | 2026-07-03T16:26:08.729+05:30
PROJECT_ID | PROJECT_NAME | Project kickoff & requirements | Hold kickoff meeting, collect detailed business, product, technical, and timeline requirements; produce a signed project brief and scope document. Done when the client has approved the project brief and success criteria. | Aarav Sharma | 2026-07-05 | 2026-07-18 | Not Started | Critical | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | UX research and wireframes | Complete user research, site information architecture, user journeys, and low-fidelity wireframes for key flows (browse, search, product, checkout). Done when wireframes and user journeys are approved and ready for visual design. | Rohan Mehta | 2026-07-19 | 2026-08-08 | Not Started | High | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | Visual design and brand assets | Deliver high-fidelity UI designs, responsive templates, and all graphic assets (banners, icons) aligned with brand; include desktop and mobile mockups. Done when visual designs are approved and assets are exported for development. | Vikram Desai | 2026-07-27 | 2026-08-21 | Not Started | High | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | Content and SEO strategy | Create product content templates, landing copy, metadata, and an SEO plan for 500 products; deliver content-ready CSVs and SEO guidelines. Done when content drafts and SEO mappings are approved and ready for import. | Simran Kaur | 2026-07-27 | 2026-08-21 | Not Started | High | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | Frontend development (UI) | Implement responsive UI using approved designs, build product listing, search, and checkout front-end components. Done when front-end is complete, integrated with staging APIs, and passes UI acceptance criteria. | Neha Verma | 2026-08-23 | 2026-10-17 | Not Started | High | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | Backend development and integration | Build APIs, database schema, authentication, payment and order systems, and integrate with front-end and any third-party services. Done when backend APIs are stable on staging, documented, and pass integration smoke tests. | Karan Singh | 2026-08-23 | 2026-10-25 | Not Started | Critical | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | Product import and CMS setup | Configure CMS/product catalog for 500 products, perform data import, set up categories, attributes, and validate product pages. Done when all products are imported, validated, and display correctly on staging. | Ananya Gupta | 2026-10-26 | 2026-11-09 | Not Started | High | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | QA, UAT, and client training | Perform end-to-end QA, accessibility and performance testing, run client UAT cycles, and deliver training materials and sessions. Done when QA issues are resolved, client signs off on UAT, and training is completed. | Priya Patel | 2026-11-10 | 2026-12-04 | Not Started | Critical | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | Launch, handover, and monitoring | Deploy the site to production, complete final verification, hand over credentials and documentation to the client, and commence monitoring and hypercare. Done when site is live, handover completed, and monitoring processes are in place. | Aarav Sharma | 2026-12-06 | 2026-12-10 | Not Started | Critical | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | Project kickoff & requirements | Hold kickoff meeting, collect detailed business, product, technical, and timeline requirements; produce a signed project brief and scope document. Done when the client has approved the project brief and success criteria. | Aarav Sharma | 2026-07-05 | 2026-07-18 | Not Started | Critical | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | UX research and wireframes | Complete user research, site information architecture, user journeys, and low-fidelity wireframes for key flows (browse, search, product, checkout). Done when wireframes and user journeys are approved and ready for visual design. | Rohan Mehta | 2026-07-19 | 2026-08-08 | Not Started | High | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | Visual design and brand assets | Deliver high-fidelity UI designs, responsive templates, and all graphic assets (banners, icons) aligned with brand; include desktop and mobile mockups. Done when visual designs are approved and assets are exported for development. | Vikram Desai | 2026-07-27 | 2026-08-21 | Not Started | High | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | Content and SEO strategy | Create product content templates, landing copy, metadata, and an SEO plan for 500 products; deliver content-ready CSVs and SEO guidelines. Done when content drafts and SEO mappings are approved and ready for import. | Simran Kaur | 2026-07-27 | 2026-08-21 | Not Started | High | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | Frontend development (UI) | Implement responsive UI using approved designs, build product listing, search, and checkout front-end components. Done when front-end is complete, integrated with staging APIs, and passes UI acceptance criteria. | Neha Verma | 2026-08-23 | 2026-10-17 | Not Started | High | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | Backend development and integration | Build APIs, database schema, authentication, payment and order systems, and integrate with front-end and any third-party services. Done when backend APIs are stable on staging, documented, and pass integration smoke tests. | Karan Singh | 2026-08-23 | 2026-10-25 | Not Started | Critical | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | Product import and CMS setup | Configure CMS/product catalog for 500 products, perform data import, set up categories, attributes, and validate product pages. Done when all products are imported, validated, and display correctly on staging. | Ananya Gupta | 2026-10-26 | 2026-11-09 | Not Started | High | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | QA, UAT, and client training | Perform end-to-end QA, accessibility and performance testing, run client UAT cycles, and deliver training materials and sessions. Done when QA issues are resolved, client signs off on UAT, and training is completed. | Priya Patel | 2026-11-10 | 2026-12-04 | Not Started | Critical | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30
PROJECT_ID | PROJECT_NAME | Launch, handover, and monitoring | Deploy the site to production, complete final verification, hand over credentials and documentation to the client, and commence monitoring and hypercare. Done when site is live, handover completed, and monitoring processes are in place. | Aarav Sharma | 2026-12-06 | 2026-12-10 | Not Started | Critical | 0 | 2026-07-04T13:34:18.898+05:30 | 2026-07-04T13:34:18.898+05:30

## Tasks Sheet
task_id | project_id | task_name | description | assigned_to | department | priority | dependency_task_id | start_date | end_date | status | progress | estimated_hours | risk_level | next_action | reminder_sent | created_at | updated_at
PROJECT_ID-KICK-T01 | PROJECT_ID | Schedule Kickoff Meeting | Arrange and schedule kickoff meetings with the client to align on project goals. Done means meeting time confirmed and invitations sent. | Aarav Sharma | Web Development | High |  | 2026-07-03 | 2026-07-03 | Not Started | 0 | 2 | Low | Contact client to propose kickoff meeting dates. | FALSE | 2026-07-03T16:59:42.346+05:30 | 2026-07-03T16:59:42.346+05:30
PROJECT_ID-KICK-T02 | PROJECT_ID | Conduct Kickoff Meeting | Run the kickoff meeting with the client to discuss business goals, user requirements, and success metrics. Done means meeting minutes documented and shared. | Aarav Sharma | Web Development | High | PROJECT_ID-KICK-T01 | 2026-07-04 | 2026-07-04 | Not Started | 0 | 3 | Medium | Prepare agenda and presentation for kickoff meeting. | FALSE | 2026-07-03T16:59:42.346+05:30 | 2026-07-03T16:59:42.346+05:30
PROJECT_ID-KICK-T03 | PROJECT_ID | Document Business Goals | Document the client's business goals clearly based on kickoff meeting outputs. Done means written goals approved internally. | Priya Patel | Web Development | High | PROJECT_ID-KICK-T02 | 2026-07-05 | 2026-07-05 | Not Started | 0 | 2 | Low | Review kickoff meeting minutes to extract business goals. | FALSE | 2026-07-03T16:59:42.346+05:30 | 2026-07-03T16:59:42.346+05:30
PROJECT_ID-KICK-T04 | PROJECT_ID | Define User Requirements | Gather and document user requirements with clear, detailed descriptions. Done means requirements document drafted and reviewed. | Priya Patel | Web Development | High | PROJECT_ID-KICK-T02 | 2026-07-05 | 2026-07-06 | Not Started | 0 | 4 | Medium | Collect additional input from stakeholders on user needs. | FALSE | 2026-07-03T16:59:42.346+05:30 | 2026-07-03T16:59:42.346+05:30
PROJECT_ID-KICK-T05 | PROJECT_ID | Prioritize Features List | Create and prioritize a list of features based on user requirements and business goals. Done means prioritized feature list reviewed and confirmed. | Priya Patel | Web Development | High | PROJECT_ID-KICK-T04 | 2026-07-07 | 2026-07-07 | Not Started | 0 | 2 | Low | Analyze requirements document to identify features. | FALSE | 2026-07-03T16:59:42.346+05:30 | 2026-07-03T16:59:42.346+05:30
PROJECT_ID-KICK-T06 | PROJECT_ID | Define Success Metrics | Define measurable success metrics for the project based on goals and requirements. Done means success metrics documented and approved by client. | Aarav Sharma | Web Development | High | PROJECT_ID-KICK-T05 | 2026-07-08 | 2026-07-08 | Not Started | 0 | 2 | Medium | Draft initial success metrics for review. | FALSE | 2026-07-03T16:59:42.346+05:30 | 2026-07-03T16:59:42.346+05:30
PROJECT_ID-KICK-T07 | PROJECT_ID | Get Client Approval on Scope | Prepare final requirements document and get client sign-off on scope and timelines. Done means signed requirements and client acceptance. | Aarav Sharma | Web Development | High | PROJECT_ID-KICK-T06 | 2026-07-09 | 2026-07-09 | Not Started | 0 | 3 | High | Send final document draft to client for review and approval. | FALSE | 2026-07-03T16:59:42.346+05:30 | 2026-07-03T16:59:42.346+05:30
PROJECT_ID-UXWJT-T01 | PROJECT_ID | Define User Journeys | Create detailed user journeys covering browse, search, product page, cart, and checkout flows. Done means user journey diagrams approved for design use. | Rohan Mehta | Design | High |  | 2026-07-10 | 2026-07-12 | Not Started | 0 | 16 | Medium | Gather requirements for user journeys and start mapping flows. | FALSE | 2026-07-03T17:00:35.544+05:30 | 2026-07-03T17:00:35.544+05:30
PROJECT_ID-UXWJT-T02 | PROJECT_ID | Create Sitemap Structure | Develop a clear sitemap illustrating the website's architecture and navigation. Done means sitemap diagram ready and approved for wireframing. | Vikram Desai | Design | High | PROJECT_ID-UXWJT-T01 | 2026-07-13 | 2026-07-14 | Not Started | 0 | 8 | Low | Review user journeys and start drafting sitemap structure. | FALSE | 2026-07-03T17:00:35.544+05:30 | 2026-07-03T17:00:35.544+05:30
PROJECT_ID-UXWJT-T03 | PROJECT_ID | Draft Low-Fidelity Wireframes | Create low-fidelity wireframes for key flows: browse, search, product page, cart, checkout. Done means wireframes ready for review and feedback. | Rohan Mehta | Design | High | PROJECT_ID-UXWJT-T02 | 2026-07-15 | 2026-07-16 | Not Started | 0 | 20 | High | Use sitemap and user journey to start wireframe sketches. | FALSE | 2026-07-03T17:00:35.544+05:30 | 2026-07-03T17:00:35.544+05:30
PROJECT_ID-UXWJT-T04 | PROJECT_ID | Review and Approve Wireframes | Conduct review sessions for wireframes and flow diagrams, gather stakeholder feedback, and approve final designs. Done means all wireframes approved for development handoff. | Aarav Sharma | Web Development | High | PROJECT_ID-UXWJT-T03 | 2026-07-17 | 2026-07-17 | Not Started | 0 | 4 | Medium | Schedule review meeting with stakeholders to present wireframes. | FALSE | 2026-07-03T17:00:35.544+05:30 | 2026-07-03T17:00:35.544+05:30
PROJECT_ID-VDBA-T01 | PROJECT_ID | Create High-Fidelity Page Designs | Develop detailed high-fidelity page designs based on wireframes and user journeys. Done means final design files are approved and ready for review. | Rohan Mehta | Design | Medium |  | 2026-07-16 | 2026-07-19 | Not Started | 0 | 32 | Medium | Gather wireframes and user journey documents for design reference. | FALSE | 2026-07-03T17:00:58.015+05:30 | 2026-07-03T17:00:58.015+05:30
PROJECT_ID-VDBA-T02 | PROJECT_ID | Design Responsive Layouts | Develop responsive page layouts that work smoothly across devices and screen sizes. Done means responsive design files are tested and finalized. | Neha Verma | Development | Medium | PROJECT_ID-VDBA-T01 | 2026-07-20 | 2026-07-22 | Not Started | 0 | 20 | Medium | Review high-fidelity designs to begin responsive layout development. | FALSE | 2026-07-03T17:00:58.015+05:30 | 2026-07-03T17:00:58.015+05:30
PROJECT_ID-VDBA-T03 | PROJECT_ID | Create Brand Asset Concepts | Develop initial concepts for banners, icons, and product image guidelines reflecting brand identity. Done means concept approval from stakeholders. | Vikram Desai | Design | Medium | PROJECT_ID-VDBA-T01 | 2026-07-20 | 2026-07-21 | Not Started | 0 | 16 | Medium | Research brand identity elements to draft asset concepts. | FALSE | 2026-07-03T17:00:58.015+05:30 | 2026-07-03T17:00:58.015+05:30
PROJECT_ID-VDBA-T04 | PROJECT_ID | Finalize Brand Assets Package | Refine and finalize brand assets including banners, icons, and guidelines for product images. Done means asset package delivered for implementation. | Vikram Desai | Design | Medium | PROJECT_ID-VDBA-T03 | 2026-07-22 | 2026-07-24 | Not Started | 0 | 16 | Low | Incorporate feedback from concept approval to finalize assets. | FALSE | 2026-07-03T17:00:58.015+05:30 | 2026-07-03T17:00:58.015+05:30
PROJECT_ID-VDBA-T05 | PROJECT_ID | Conduct Design QA and Revisions | Perform quality assurance on designs and assets, make necessary revisions based on feedback. Done means all issues are resolved and files are final. | Rohan Mehta | Design | Medium | PROJECT_ID-VDBA-T04 | 2026-07-25 | 2026-07-26 | Not Started | 0 | 12 | Medium | Collect QA feedback and begin revision process. | FALSE | 2026-07-03T17:00:58.015+05:30 | 2026-07-03T17:00:58.015+05:30
PROJECT_ID-VDBA-T06 | PROJECT_ID | Deliver Final Design Files & Assets | Compile and deliver final high-fidelity designs, responsive layouts, and brand asset package for implementation. Done means all files are delivered to the implementation team. | Aarav Sharma | Web Development | Medium | PROJECT_ID-VDBA-T05 | 2026-07-27 | 2026-07-27 | Not Started | 0 | 4 | Low | Prepare delivery package and notify implementation team. | FALSE | 2026-07-03T17:00:58.015+05:30 | 2026-07-03T17:00:58.015+05:30
PROJECT_ID-FRONT-T01 | PROJECT_ID | Setup React Project Infrastructure | Initialize the React project setup including build tools, folder structure, and dependencies. Done means a fully configured and runnable React base project. | Neha Verma | Development | Critical |  | 2026-07-20 | 2026-07-23 | Not Started | 0 | 16 | Medium | Create a new React app with necessary dependencies and folder structure. | FALSE | 2026-07-03T17:01:52.773+05:30 | 2026-07-03T17:01:52.773+05:30
PROJECT_ID-FRONT-T02 | PROJECT_ID | Implement Responsive UI Components | Develop reusable responsive UI components based on design assets with React. Done means components are tested for responsiveness and consistent with designs. | Neha Verma | Development | Critical | PROJECT_ID-FRONT-T01 | 2026-07-24 | 2026-07-30 | Not Started | 0 | 40 | High | Review design assets and begin coding key UI components. | FALSE | 2026-07-03T17:01:52.773+05:30 | 2026-07-03T17:01:52.773+05:30
PROJECT_ID-FRONT-T03 | PROJECT_ID | Create Client-Side Interactions | Implement client-side interactions and state management for UI components using React hooks and context. Done means all interactions work smoothly as per UI/UX specs. | Neha Verma | Development | Critical | PROJECT_ID-FRONT-T02 | 2026-07-31 | 2026-08-05 | Not Started | 0 | 32 | High | Define interaction requirements and implement state management logic. | FALSE | 2026-07-03T17:01:52.773+05:30 | 2026-07-03T17:01:52.773+05:30
PROJECT_ID-FRONT-T04 | PROJECT_ID | Integrate APIs with Frontend | Connect UI components to backend APIs and handle data flow and error states. Done means data integration is stable and user flows function with live API. | Ananya Gupta | Development | Critical | PROJECT_ID-FRONT-T03 | 2026-08-06 | 2026-08-10 | Not Started | 0 | 24 | High | Analyze API specs and begin coding frontend API calls. | FALSE | 2026-07-03T17:01:52.773+05:30 | 2026-07-03T17:01:52.773+05:30
PROJECT_ID-FRONT-T05 | PROJECT_ID | Visual Review and Design QA | Perform visual and UX review to ensure the frontend matches design assets perfectly. Done means all visual glitches are fixed and UI matches approved designs. | Rohan Mehta | Design | Critical | PROJECT_ID-FRONT-T04 | 2026-08-11 | 2026-08-13 | Not Started | 0 | 16 | Medium | Compare implemented UI against design mockups and document issues. | FALSE | 2026-07-03T17:01:52.773+05:30 | 2026-07-03T17:01:52.773+05:30
PROJECT_ID-FRONT-T06 | PROJECT_ID | Deploy Frontend to Staging Environment | Deploy the completed frontend application to the staging environment for further testing. Done means the app is accessible in staging and passes smoke tests. | Aarav Sharma | Web Development | Critical | PROJECT_ID-FRONT-T05 | 2026-08-14 | 2026-08-17 | Not Started | 0 | 12 | Medium | Prepare deployment scripts and initiate staging deployment. | FALSE | 2026-07-03T17:01:52.773+05:30 | 2026-07-03T17:01:52.773+05:30
PROJECT_ID-BEINT-T01 | PROJECT_ID | Design Database Schema | Create a comprehensive database schema to support e-commerce operations including products, users, orders, and transactions. Done means schema reviewed and finalized. | Karan Singh | Development | Critical |  | 2026-07-27 | 2026-07-30 | Not Started | 0 | 24 | Medium | Draft initial database schema diagrams and review with team. | FALSE | 2026-07-03T17:03:29.592+05:30 | 2026-07-03T17:03:29.592+05:30
PROJECT_ID-BEINT-T02 | PROJECT_ID | Build Backend APIs | Develop backend APIs to support frontend functionality, covering user management, product catalog, orders, and payments. Done means APIs are implemented and passed initial tests. | Karan Singh | Development | Critical | PROJECT_ID-BEINT-T01 | 2026-07-31 | 2026-08-07 | Not Started | 0 | 48 | High | Set up project repository and start API endpoint implementation. | FALSE | 2026-07-03T17:03:29.592+05:30 | 2026-07-03T17:03:29.592+05:30
PROJECT_ID-BEINT-T03 | PROJECT_ID | Implement Authentication System | Develop secure user authentication mechanisms including registration, login, password reset, and token management. Done means secure auth system integrated and tested. | Karan Singh | Development | Critical | PROJECT_ID-BEINT-T02 | 2026-08-08 | 2026-08-12 | Not Started | 0 | 24 | High | Design authentication workflow and security protocols. | FALSE | 2026-07-03T17:03:29.592+05:30 | 2026-07-03T17:03:29.592+05:30
PROJECT_ID-BEINT-T04 | PROJECT_ID | Integrate Payment Gateway | Connect and configure payment gateway APIs to allow secure payment processing. Done means payment gateway test transactions succeed in staging. | Karan Singh | Development | Critical | PROJECT_ID-BEINT-T03 | 2026-08-13 | 2026-08-17 | Not Started | 0 | 16 | High | Set up payment gateway sandbox and obtain API credentials. | FALSE | 2026-07-03T17:03:29.592+05:30 | 2026-07-03T17:03:29.592+05:30
PROJECT_ID-BEINT-T05 | PROJECT_ID | Develop Third-Party Integrations | Build integrations with third-party services such as shipping, notifications, and analytics. Done means integrations tested and correctly functioning. | Ananya Gupta | Development | Critical | PROJECT_ID-BEINT-T04 | 2026-08-18 | 2026-08-22 | Not Started | 0 | 20 | Medium | Identify required third-party APIs and review documentation. | FALSE | 2026-07-03T17:03:29.592+05:30 | 2026-07-03T17:03:29.592+05:30
PROJECT_ID-BEINT-T06 | PROJECT_ID | Deploy Backend to Staging | Deploy the complete backend including APIs, authentication, payment gateway, and integrations to the staging environment. Done means deployment successful with no critical issues. | Karan Singh | Development | Critical | PROJECT_ID-BEINT-T05 | 2026-08-23 | 2026-08-24 | Not Started | 0 | 8 | Medium | Prepare staging environment and deployment scripts. | FALSE | 2026-07-03T17:03:29.592+05:30 | 2026-07-03T17:03:29.592+05:30
PROJECT_ID-PCMS-T01 | PROJECT_ID | Define Product Data Model | Configure the product data model to support shoe catalog details. Done means model schema finalized and documented. | Ananya Gupta | Development | High |  | 2026-08-03 | 2026-08-06 | Not Started | 0 | 16 | Medium | Review product requirements and start data model design. | FALSE | 2026-07-03T17:04:00.890+05:30 | 2026-07-03T17:04:00.890+05:30
PROJECT_ID-PCMS-T02 | PROJECT_ID | Import Initial Shoe Catalog | Import shoe catalog data into the configured product model. Done means full catalog uploaded and validated for accuracy. | Karan Singh | Development | High | PROJECT_ID-PCMS-T01 | 2026-08-07 | 2026-08-11 | Not Started | 0 | 20 | Medium | Prepare import script and test with sample data. | FALSE | 2026-07-03T17:04:00.890+05:30 | 2026-07-03T17:04:00.890+05:30
PROJECT_ID-PCMS-T03 | PROJECT_ID | Set Up CMS User Access | Configure CMS user roles and permissions for content management. Done means CMS users created and access controls tested. | Ananya Gupta | Development | High | PROJECT_ID-PCMS-T02 | 2026-08-12 | 2026-08-14 | Not Started | 0 | 10 | Low | Define user roles and access levels for CMS. | FALSE | 2026-07-03T17:04:00.890+05:30 | 2026-07-03T17:04:00.890+05:30
PROJECT_ID-PCMS-T04 | PROJECT_ID | Develop Pricing & Variant Controls | Implement workflows for pricing management and product variants within CMS. Done means pricing rules and variants setup are functional and documented. | Neha Verma | Development | High | PROJECT_ID-PCMS-T03 | 2026-08-15 | 2026-08-18 | Not Started | 0 | 18 | Medium | Gather pricing structure requirements to begin development. | FALSE | 2026-07-03T17:04:00.890+05:30 | 2026-07-03T17:04:00.890+05:30
PROJECT_ID-PCMS-T05 | PROJECT_ID | Document Content Entry Workflows | Create detailed documentation for CMS content entry workflows to guide users. Done means documentation is complete and reviewed. | Priya Patel | Web Development | High | PROJECT_ID-PCMS-T04 | 2026-08-19 | 2026-08-21 | Not Started | 0 | 12 | Low | Outline key steps in content entry process for documentation. | FALSE | 2026-07-03T17:04:00.890+05:30 | 2026-07-03T17:04:00.890+05:30
PROJECT_ID-SEOCT-T01 | PROJECT_ID | Research SEO Keywords | Identify relevant SEO keywords and phrases for product descriptions and landing pages. Done means a finalized keyword list is approved for content use. | Simran Kaur | Content | Medium |  | 2026-08-10 | 2026-08-12 | Not Started | 0 | 8 | Low | Begin compiling SEO keywords based on product research. | FALSE | 2026-07-03T17:04:29.120+05:30 | 2026-07-03T17:04:29.120+05:30
PROJECT_ID-SEOCT-T02 | PROJECT_ID | Draft Product Descriptions | Write SEO-optimized product descriptions using approved keywords. Done means draft descriptions for all products are ready for review. | Simran Kaur | Content | Medium | PROJECT_ID-SEOCT-T01 | 2026-08-13 | 2026-08-16 | Not Started | 0 | 16 | Medium | Start writing drafts for each product description. | FALSE | 2026-07-03T17:04:29.120+05:30 | 2026-07-03T17:04:29.120+05:30
PROJECT_ID-SEOCT-T03 | PROJECT_ID | Create Landing Page Copy | Develop SEO-focused copy for key landing pages aligned with product descriptions and keywords. Done means content is ready for initial internal review. | Simran Kaur | Content | Medium | PROJECT_ID-SEOCT-T02 | 2026-08-17 | 2026-08-19 | Not Started | 0 | 12 | Medium | Outline landing pages and draft copy for each. | FALSE | 2026-07-03T17:04:29.120+05:30 | 2026-07-03T17:04:29.120+05:30
PROJECT_ID-SEOCT-T04 | PROJECT_ID | Write Meta Tags | Compose meta titles and descriptions for products and landing pages to enhance SEO. Done means meta tags uploaded to staging environment. | Simran Kaur | Content | Medium | PROJECT_ID-SEOCT-T03 | 2026-08-20 | 2026-08-21 | Not Started | 0 | 6 | Low | Collect finalized titles and descriptions to start meta tags writing. | FALSE | 2026-07-03T17:04:29.120+05:30 | 2026-07-03T17:04:29.120+05:30
PROJECT_ID-SEOCT-T05 | PROJECT_ID | Develop Initial Blog Content | Create initial SEO-optimized blog and landing content for launch. Done means blog content is drafted and uploaded to staging for review. | Simran Kaur | Content | Medium | PROJECT_ID-SEOCT-T04 | 2026-08-22 | 2026-08-24 | Not Started | 0 | 14 | Medium | Identify blog topics aligned with SEO keywords to begin drafting. | FALSE | 2026-07-03T17:04:29.120+05:30 | 2026-07-03T17:04:29.120+05:30
PROJECT_ID-QAT-T01 | PROJECT_ID | Develop Testing Strategy | Create a comprehensive testing plan covering functional, cross-browser, performance, and payment flow testing. Done means testing strategy document approved. | Priya Patel | Web Development | Critical |  | 2026-08-17 | 2026-08-18 | Not Started | 0 | 12 | Medium | Draft initial testing strategy outline. | FALSE | 2026-07-03T17:05:13.444+05:30 | 2026-07-03T17:05:13.444+05:30
PROJECT_ID-QAT-T02 | PROJECT_ID | Functional Testing Execution | Perform functional testing to verify all features meet requirements without critical issues. Done means all critical functional tests passed or issues logged. | Aarav Sharma | Web Development | Critical | PROJECT_ID-QAT-T01 | 2026-08-19 | 2026-08-22 | Not Started | 0 | 20 | High | Set up test environment for functional testing. | FALSE | 2026-07-03T17:05:13.444+05:30 | 2026-07-03T17:05:13.444+05:30
PROJECT_ID-QAT-T03 | PROJECT_ID | Cross-Browser Testing | Test the website across major browsers and devices for compatibility issues. Done means all critical browser issues resolved or logged. | Neha Verma | Development | Critical | PROJECT_ID-QAT-T02 | 2026-08-23 | 2026-08-24 | Not Started | 0 | 12 | Medium | Gather browser versions and devices for testing. | FALSE | 2026-07-03T17:05:13.444+05:30 | 2026-07-03T17:05:13.444+05:30
PROJECT_ID-QAT-T04 | PROJECT_ID | Performance Testing | Conduct performance tests to assess load times and responsiveness. Done means performance thresholds met and issues logged if any. | Karan Singh | Development | Critical | PROJECT_ID-QAT-T03 | 2026-08-25 | 2026-08-26 | Not Started | 0 | 14 | High | Prepare performance testing scripts and scenarios. | FALSE | 2026-07-03T17:05:13.444+05:30 | 2026-07-03T17:05:13.444+05:30
PROJECT_ID-QAT-T05 | PROJECT_ID | Payment Flow Testing | Test all payment processes for correctness and reliability. Done means all critical payment scenarios validated and no blocker issues remain. | Ananya Gupta | Development | Critical | PROJECT_ID-QAT-T04 | 2026-08-27 | 2026-08-28 | Not Started | 0 | 16 | High | Identify key payment scenarios to test. | FALSE | 2026-07-03T17:05:13.444+05:30 | 2026-07-03T17:05:13.444+05:30
PROJECT_ID-QAT-T06 | PROJECT_ID | Log Issues and Track Bugs | Document all issues found during testing in the bug tracking system. Done means all critical issues logged with reproduction steps and severity. | Priya Patel | Web Development | Critical | PROJECT_ID-QAT-T05 | 2026-08-27 | 2026-08-29 | Not Started | 0 | 18 | High | Set up bug tracking tools and templates. | FALSE | 2026-07-03T17:05:13.444+05:30 | 2026-07-03T17:05:13.444+05:30
PROJECT_ID-QAT-T07 | PROJECT_ID | Resolve Critical Bugs | Fix all critical and blocker bugs identified in testing. Done means no critical/blocker issues remain in the system. | Neha Verma | Development | Critical | PROJECT_ID-QAT-T06 | 2026-08-30 | 2026-08-31 | Not Started | 0 | 24 | High | Prioritize bugs for immediate resolution. | FALSE | 2026-07-03T17:05:13.444+05:30 | 2026-07-03T17:05:13.444+05:30
PROJECT_ID-LDHT-T01 | PROJECT_ID | Deploy Site to Production | Deploy the completed website to the production server. Done means the site is live and accessible to users. | Neha Verma | Development | Critical |  | 2026-09-01 | 2026-09-01 | Not Started | 0 | 4 | Medium | Prepare production environment and assets for deployment. | FALSE | 2026-07-03T17:05:38.208+05:30 | 2026-07-03T17:05:38.208+05:30
PROJECT_ID-LDHT-T02 | PROJECT_ID | Run Final Smoke Tests | Conduct final smoke tests on the production site to verify basic functionality and performance. Done means all critical tests pass without issues. | Karan Singh | Development | Critical | PROJECT_ID-LDHT-T01 | 2026-09-01 | 2026-09-02 | Not Started | 0 | 3 | High | Define smoke test scripts and scenarios. | FALSE | 2026-07-03T17:05:38.208+05:30 | 2026-07-03T17:05:38.208+05:30
PROJECT_ID-LDHT-T03 | PROJECT_ID | Complete Deployment Checklist | Verify all deployment steps and configurations are completed as per the checklist. Done means checklist items are all marked complete. | Priya Patel | Web Development | Critical | PROJECT_ID-LDHT-T02 | 2026-09-02 | 2026-09-02 | Not Started | 0 | 2 | Medium | Review deployment checklist and assign any pending items. | FALSE | 2026-07-03T17:05:38.208+05:30 | 2026-07-03T17:05:38.208+05:30
PROJECT_ID-LDHT-T04 | PROJECT_ID | Prepare Credentials & Documentation | Create and organize all credentials, access information, and documentation for client handover. Done means client has received all necessary info and docs. | Aarav Sharma | Web Development | Critical | PROJECT_ID-LDHT-T03 | 2026-09-02 | 2026-09-03 | Not Started | 0 | 3 | Low | Gather all credential details and draft documentation. | FALSE | 2026-07-03T17:05:38.208+05:30 | 2026-07-03T17:05:38.208+05:30
PROJECT_ID-LDHT-T05 | PROJECT_ID | Client Acceptance & Launch Support | Obtain final client acceptance of the live site and provide a short support window post-launch. Done means client sign-off received and support completed. | Aarav Sharma | Web Development | Critical | PROJECT_ID-LDHT-T04 | 2026-09-03 | 2026-09-03 | Not Started | 0 | 2 | Medium | Schedule client meeting for acceptance and support discussion. | FALSE | 2026-07-03T17:05:38.208+05:30 | 2026-07-03T17:05:38.208+05:30

## Notification
notification_id | task_id | project_id | recipient | notification_type | message | status | sent_at | created_at
19f27e1f7f825fd4 | PROJECT_ID-KICK-T01 | PROJECT_ID | aarav.sharma@company.com | Email | <p>Dear Aarav,</p><p>This is a friendly reminder about the task to schedule the kickoff meeting, which is due today, July 3, 2026. It's important for us to get this meeting on the calendar to keep the project on track.</p><p>Please let us know if you are facing any challenges or if there’s anything we can assist you with to move this forward.</p><p>Warm regards,<br>The Project Team</p> | Email sent | 2026-07-03T17:16:54.242+05:30 | 2026-07-03T17:16:54.242+05:30

## Task Tracker
project_id | task_id | task_name | start_date | end_date | progress | dependency | assigned_to | status

## Team Members
Employee_ID | Employee_Name | Email | Role | Department | Manager | Location | Role
WEB001 | Aarav Sharma | aarav.sharma@company.com | Project Director | Web Development | None | Ahmedabad | Oversees website projects, client communication, and delivery timelines.
WEB002 | Priya Patel | priya.patel@company.com | Project Manager | Web Development | Aarav Sharma | Ahmedabad | Manages project planning, resources, and coordination between teams.
WEB003 | Rohan Mehta | rohan.mehta@company.com | UI/UX Designer | Design | Priya Patel | Ahmedabad | Creates wireframes, user journeys, and interface designs for websites.
WEB004 | Neha Verma | neha.verma@company.com | Frontend Developer | Development | Priya Patel | Mumbai | Develops responsive user interfaces using HTML, CSS, JavaScript, and React.
WEB005 | Karan Singh | karan.singh@company.com | Backend Developer | Development | Priya Patel | Delhi | Builds APIs, databases, authentication systems, and server-side logic.
WEB006 | Ananya Gupta | ananya.gupta@company.com | Full Stack Developer | Development | Priya Patel | Bangalore | Handles both frontend and backend development tasks across projects.
WEB007 | Vikram Desai | vikram.desai@company.com | Graphic Designer | Design | Rohan Mehta | Ahmedabad | Designs website graphics, banners, icons, and brand assets.
WEB008 | Simran Kaur | simran.kaur@company.com | Content Writer | Content | Priya Patel | Chandigarh | Creates website copy, landing page content, blogs, and SEO-focused content.

## Progress Checker
Total Projects
Total Tasks
Completed Tasks
Pending Tasks
Delayed Tasks
High Risk Tasks
Completion Percentage

## Agent Logs
timestamp | agent_name | action | project_id | task_id | input | output | status
2026-07-03T17:16:54.242+05:30 | Task. Tracker | Email Sent | PROJECT_ID | PROJECT_ID-KICK-T01 | Aarav Sharma | <p>Dear Aarav,</p><p>This is a friendly reminder about the task to schedule the kickoff meeting, which is due today, July 3, 2026. It's important for us to get this meeting on the calendar to keep the project on track.</p><p>Please let us know if you are facing any challenges or if there’s anything we can assist you with to move this forward.</p><p>Warm regards,<br>The Project Team</p> | Email Sent

## Prompt
You are a Project Planning Agent. Your job is to break a project request into a clear, ordered set of milestones and return them as structured data that maps exactly to a task-tracking spreadsheet. ## INPUTS You receive: 1. A project request from chat describing what needs to be planned (goal, scope, any constraints, deadlines). 3. CURRENT_TIMESTAMP: {{ $now }} 4. AVAILABLE_EMPLOYEES (assign owners ONLY from this list): {{ JSON.stringify($data, null, 2) }} Each employee has: Employee_ID, Employee_Name, Email, Role, Department, Manager, Location. ## YOUR TASK - Decompose the project into 4–10 logical, sequential milestones. Each milestone is a meaningful phase or deliverable, not a tiny sub-task. - Order them so dependencies make sense (a milestone's start should follow the end of what it depends on). - Assign a realistic timeline. Build a sensible schedule starting from today (CURRENT_TIMESTAMP) unless the request specifies a start date. Milestones may overlap if they can run in parallel. - Assign exactly one Owner per milestone, chosen from AVAILABLE_EMPLOYEES. Match the owner to the milestone based on their Role and Department (e.g. design work → a designer, backend work → an engineer). Use the exact Employee_Name string from the list. - Write a concise 1–2 sentence Description for each milestone explaining what "done" looks like. ## FIELD RULES - Project_id: use PROJECT_ID for every row. - Project_name: use PROJECT_NAME for every row. - Milestones: a short title (3–8 words). - Description: 1–2 sentences, outcome-focused. - Owner: must exactly match an Employee_Name from AVAILABLE_EMPLOYEES. Never invent a name. - Start_date / End_date: ISO 8601 date format (YYYY-MM-DD). End_date must be on or after Start_date. - Status: always "Not Started" for newly planned milestones. - Priority: one of "Low", "Medium", "High", "Critical" based on impact and urgency. - Progress_percentage: always 0 for new milestones. - Created_at / Updated_at: set both to CURRENT_TIMESTAMP (ISO 8601). ## CONSTRAINTS - Do not assign an owner who is not in AVAILABLE_EMPLOYEES. - Do not add commentary, explanations, or markdown. Return only the structured object defined by the output schema. - Every milestone object must contain all fields, with no nulls. | { "tasks": [ { "task_id": "KIS-001-RES-T01", "project_id": "KIS-001", "task_name": "Draft farmer survey questionnaire", "description": "Write a 12-15 question survey covering scheme awareness and access barriers. Done when the questionnaire is reviewed and approved.", "assigned_to": "Yash Patel", "department": "Marketing", "priority": "High", "dependency_task_id": "", "start_date": "2026-06-20", "end_date": "2026-06-23", "status": "Not Started", "progress": 0, "estimated_hours": 8, "risk_level": "Low", "next_action": "Outline the survey sections and key questions.", "reminder_sent": false, "created_at": "2026-06-18T19:11:45.055+05:30", "updated_at": "2026-06-18T19:11:45.055+05:30" }, { "task_id": "KIS-001-RES-T02", "project_id": "KIS-001", "task_name": "Conduct farmer interviews", "description": "Run the approved survey with at least 30 target farmers across regions. Done when responses are collected and logged.", "assigned_to": "Kavya Rao", "department": "Marketing", "priority": "High", "dependency_task_id": "KIS-001-RES-T01", "start_date": "2026-06-24", "end_date": "2026-07-01", "status": "Not Started", "progress": 0, "estimated_hours": 24, "risk_level": "Medium", "next_action": "Identify and contact the first batch of farmers.", "reminder_sent": false, "created_at": "2026-06-18T19:11:45.055+05:30", "updated_at": "2026-06-18T19:11:45.055+05:30" } ] } | You are a Task Reminder Agent. You write a short, professional reminder email to an employee about a task they have not yet completed. Your tone is polite, supportive, and clear — a helpful nudge, never a reprimand. ## INPUTS You receive one task that is due today or overdue: - ASSIGNEE_NAME: {{ $('Get row(s) in sheet').item.json.assigned_to }} - TASK_NAME: {{ $('Get row(s) in sheet').item.json.task_name }} - PROJECT_ID: {{ $('Get row(s) in sheet').item.json.project_id }} - DUE_DATE: {{ $('Get row(s) in sheet').item.json.end_date }} - CURRENT_DATE: {{ $today.toISODate() }} ## YOUR TASK Write a reminder email to ASSIGNEE_NAME about TASK_NAME. Determine the situation by comparing DUE_DATE to CURRENT_DATE: - If DUE_DATE equals CURRENT_DATE: the task is due today. Frame it as a friendly heads-up. - If DUE_DATE is before CURRENT_DATE: the task is overdue. Mention by how many days, but stay courteous and solution-focused. The email should: - Open by addressing the person by their first name. - State clearly which task this is about and its due date. - Briefly remind them what the task involves (one line, from TASK_DESCRIPTION). - Reference the suggested next step (NEXT_ACTION) to make it easy to act. - If PRIORITY is "High" or "Critical", or RISK_LEVEL is "High", gently convey that this one is time-sensitive — without pressure or blame. - Invite them to reply with a status update or to flag any blockers. - Close warmly and professionally. ## RULES - Keep the body under 130 words. Be concise and respectful of their time. - Do not guilt-trip, scold, or use accusatory language ("you failed to...", "you were supposed to..."). Assume good intent. - Do not invent facts, deadlines, or details not present in the inputs. - Use plain, natural language. No markdown, no bullet points in the email body. - Sign off as "The Project Team" (no fake individual name). - Return only the structured object defined by the output schema — no commentary.
{ "milestones": [ { "Project_id": "KIS-001", "Project_name": "Kisaniyat", "Milestones": "Market research and farmer needs analysis", "Description": "Survey target farmers to identify which government schemes they struggle to access and why. Done when a prioritized list of scheme categories and pain points is documented.", "Owner": "Yash Patel", "Start_date": "2026-06-20", "End_date": "2026-07-04", "Status": "Not Started", "Priority": "High", "Progress_percentage": 0, "Created_at": "2026-06-18T19:11:45.055+05:30", "Updated_at": "2026-06-18T19:11:45.055+05:30" }, { "Project_id": "KIS-001", "Project_name": "Kisaniyat", "Milestones": "Content strategy for scheme awareness", "Description": "Define the messaging, channels, and content calendar for educating farmers about relevant schemes. Done when an approved content plan covering blogs and social media exists.", "Owner": "Devansh Jain", "Start_date": "2026-07-05", "End_date": "2026-07-20", "Status": "Not Started", "Priority": "Medium", "Progress_percentage": 0, "Created_at": "2026-06-18T19:11:45.055+05:30", "Updated_at": "2026-06-18T19:11:45.055+05:30" } ] }
You are a Task Generation Agent. Given a single project milestone, you break it into concrete, actionable tasks and return them as structured data that maps exactly to a task-tracking spreadsheet. ## INPUTS You receive one milestone to decompose: -PROJECT_ID: -MILESTONE_NAME: -MILESTONE_DESCRIPTION: -MILESTONE_OWNER: -MILESTONE_PRIORITY: -MILESTONE_START: -MILESTONE_END: -CURRENT_TIMESTAMP: {{ $now }} - AVAILABLE_EMPLOYEES (assign tasks ONLY to people from this list): {{ JSON.stringify($('Employees').first().json.data, null, 2) }} Each employee has: Employee_ID, Employee_Name, Email, Role, Department, Manager, Location. ## YOUR TASK - Break this milestone into 3–8 concrete tasks. Each task is a single piece of work someone can pick up and complete, not a vague theme. - Order tasks logically. Where one task must finish before another can start, record that with dependency_task_id. - Keep every task's dates inside the milestone window (between MILESTONE_START and MILESTONE_END). Sequence dependent tasks so a task starts on or after its dependency ends. - Assign each task to the most suitable person from AVAILABLE_EMPLOYEES, matching their Role and Department to the work. The MILESTONE_OWNER is the default lead, but delegate to others where their role fits better. ## FIELD RULES - task_id: generate a unique id using the pattern {PROJECT_ID}-{milestone-slug}-T{NN}, where milestone-slug is a 3-5 letter abbreviation of the milestone and NN is a zero-padded sequence (T01, T02...). IDs must be unique within this milestone. - project_id: use PROJECT_ID for every task. - task_name: short title (3–8 words). - description: 1–2 sentences describing the work and what "done" means. - assigned_to: must exactly match an Employee_Name from AVAILABLE_EMPLOYEES. Never invent a name. - department: the Department of the assigned person, taken from AVAILABLE_EMPLOYEES. - priority: one of "Low", "Medium", "High", "Critical". - dependency_task_id: the task_id of the task that must finish first. Use an empty string "" if the task has no dependency. - start_date / end_date: ISO 8601 date (YYYY-MM-DD), within the milestone window. end_date on or after start_date. - status: always "Not Started" for newly generated tasks. - progress: always 0 for new tasks. - estimated_hours: a realistic whole or half number of hours to complete the task. - risk_level: one of "Low", "Medium", "High", reflecting likelihood of delay or difficulty. - next_action: one short sentence stating the immediate first step to start the task. - reminder_sent: always false for new tasks. - created_at / updated_at: set both to CURRENT_TIMESTAMP (ISO 8601). ## CONSTRAINTS - Assign only people present in AVAILABLE_EMPLOYEES; department must match that person's record. - Every task object must contain all fields, with no nulls (use "" for dependency_task_id when none). - Return only the structured object defined by the output schema. No commentary, no markdown.